## Form SCMP 7.5 a Rev B
SCMP Form 7.5 (a) WT Package Analysis - Complete prior to approval as part of developing the work transfer project strategy
Considerations Applicable to all Work Transfers- Any non-addressable item must be moved to Project Risk Assessment
Number
| Category | Yes/No | TGI WT Potential Actions(s) | Base Acceptability | SCMP 7.5a Comments
1 | Process |  | TGI WT Potential Actions(s) | Base Acceptability | Comments | Suggested Actions
2 | Has the risk assessment (SCMP 7.4) been completed to support the team charter? |  | Yes: Copy SCMP 7.4 Risk Assessment into WT Folder No: Reject WT until reason provided a Risk Assessment not performed
3 | Have lesssons learned from previous projects been considered? |  | Yes: Review Lessons Learned and add mitigation to Form SCMP 7.5c No: Consult with Lead of prior project (if applicable) add mitigation to Form SCMP 7.5c
4 | Have all open actions from SCMP 7.4 review been satisfactorily closed or will be transfered to SCMP 7.5 f |  | Update Form SCMP 7.5 f
5 | Potential New Source(s) | Yes/No | TGI WT Potential Actions(s) | Base Acceptability | SCMP 7.5a Comments | Suggested Actions
6 | Is there a history of non-conformance at current source or of similar parts at proposed source(s)? |  | Consult Quality System for validation of non-conformance Risk. If risk identified add to Form SCMP 7.5c for communication to new source
7 | Will the project follow the PSR/SSR Process? |  | Formally request completion of a sourcing board process | Written confirmation (email acceptable) from site purchasing that SCMP 7.4 will not be followed |  | "no","Review with Site Purchasing Lead and justify why process not used.
8 | Do the sources have quality management systems that meet Site requirements? |  | Confirm supplier is on the site AVL and obtain a copy of AS9100 or ISO accreditation | Confirmation supplier is on site AVL |  | "no","Review available data with Site Quality to determine supplier acceptablility
9 | If required, are the sources registered with the US State Department for the production of defense articles (US domestic) or are Manufacturing License Agreements in place that cover the transitioning parts (foreign sources)? |  | Confirm if any potential sources are registered with the US State Dept | Confirmation of sources registered if required |  | "no": Review with export representative (e.g. empowered official) for military or commercial application and license determination and verify the supplier's registration status with the DDTC. This action Must be done prior to any quoting activity
10 | Do all sources have a signed and valid NDA (Non Disclosure Agreement) with Triumph Group? |  | Confirm that all sources have a valid NDA | Valid NDA in place |  | "no","An NDA should be executed with each potential source prior to proceeding with any quoting activity.
11 | Are there any LTA clauses with the current source (Production or aftermarket) that could affect the work transfer? (for example) (a) Exclusivity (i.e., has TGI agreed that the existing supplier will be an exclusive supplier for the part that TGI is looking to transition to a new supplier?) (b) Requirements language (i.e., is TGI required to purchase a certain percentage of its requirements from the existing supplier?) (c) Termination for Convenience – confirm such right exists for TGI and that any responsibility for loss profits is excluded. |  | Request data from site sourcing that there are no LTA clauses affecting the proposed parts for transfer | Review of valid LTA to confirm no commecial clauses that affect a work transfer |  | "yes","Working with Supply Chain Management Contract Specialist, develop mitigation strategy
12 | Will the transfer package require Customer Approval/Notification? (internal and external) |  | Confirm with project nominated Program Manager that all customer approvals/notifications have been initiated | Initiation, if required, of customer approvals/notifications with |  | "yes","Send Customer Notification Letter and consider VOC-formal or informal or other follow-up to ensure Customer stakeholders are informed and Customer requirements are understood. For Consolidations Use TOW Comliance Matrix
13 | Will the FAA (or specific regulatory body) require notification or approval of the source transition? |  | Confirm with project nominated Program Manager of FAA (or any othr specific regulatory body) approval/notification is required | Initiation, if required, of FAA (or any other specific regulatory body) approvals/notifications with |  | "yes","Review requirement and notify/obtain approval as required (refer to FAA category parts listing for additional guidance).
14 | Product |  | TGI WT Potential Actions(s) | Base Acceptability | Comments | Suggested Actions
15 | Have the parts included in this transfer been reviewed to determine if they are included on an existing work transfer or projected to be awarded to a supplier with other active transitions ? |  | Confirm parts are not included in another work transfer - or if they are confirm with site sourcing that this is still a valid work transfer | Confirmation from site to show validity of transfer |  | "yes","Align strategies and Work transfer plans prior to proceeding.
16 | Is the commodity (i.e. part or equipment) and technical data classified for export? |  | Confirm drawings are classifed by export control | Confirm drawings are classifed by export control |  | "no","Obtain export jurisdiction and classification prior to proceeding with project. This item must be complete prior to any quoting activity. For Consolidations, if any product is ITAR, submit Material Changes - 5-Day Notification (Per ITAR 122.4(a)))
17 | Is the Buy American Act (or any other applicable legistaltion - for example Berry Amendment) applicable to parts in this transition (confirm with contract specialist in answering this question - this applies to parts purchased/manufacture for a government program, even if they are dual use)? (a) If TGI certified that it will comply with the Buy American Act, is the new supplier located outside of the U.S., for Buy American considerations, and if so, do any exceptions or waivers apply (check FAR 52.225)? (b) Are there any Specialty Metal in the part to be supplied by the new supplier (check DFARs 252.225-7008 and 252.225-7009), and if so, do any exceptions apply? |  | Work with Contracts (Enterprise or Site) to confirm applicability of Buy American Act Did TGI certify it would comply and does the product have any speciality metals covered by DFARs? | Written confirmation (email acceptable) of any applicability |  | "yes","Identify end use of part and if it is sold is a Spare to determine if any Buy American/Specialty Metals concerns at Spare part or LRU/end item level
18 | Is the part Source Controlled/Customer directed/Proprietary/Sole Source part (i.e. the supplier is called out on drawing or specification)? See note |  | Work with Engineering and contracts to ascertain if there are any controls that need to be followed | Confrimation that the part(s) are acceptable for work transfer |  | "yes","Determine reason for specified source, verify contract requirements. Initiate engineering change notice, if applicable.
19 | Are there Intellectual Property concerns related to the manufacture of this product? (refer to hover note for explanation - detailed questions that must be considered during risk assessment, prior to any drawings/specs being sent to prospective sources) |  | Work Transfer to validate IP concerns addressed in SCMP 7.4 before proceding with WT |  |  | "yes","Address all IP considerations associated with proposed transfer prior to initiating quote activity. This may include a signed NDA and/or limiting material flowed to the potential new sources
20 | Is the transition part flight safety/flight critical?
21 | Resources |  | TGI WT Potential Actions(s) | Base Acceptability | Comments | Suggested Actions
22 | Are there any travel concerns specific to this project? |  | Are any of the suppliers in a location that is on a "no travel" list (Official or TGI) | Confirmation that potential suppliers are not on a "no travel" list |  | "yes","Assess safety risks and willingness of traveler to go to high risk area.
23 | Is funding required to execute this transition? For example - Tooling, NRE, Travel, ME Support etc |  | Work Transfer to validate funding (if applicable) has been secured before proceding with WT |  |  | "yes","Submit appropriate funding request including NRE as required and gain necessary approvals.
Note on B22: Confirm if Special Processes or lower level components are source controlled
Note on B23: 1) Does another entity besides TGI own any IP related to the product/drawings/specs (i.e., did TGIsolely design/create or was the supplier/another entity involved in the design)? 2) Did TGI use/rely on any information, not owned or created by TGI, in creating the TGI drawing/spec (e.g., did TGI use information from a supplier’s drawing, specification, data sheet, or other supplier provided document into the subject TGI drawing/spec)? 3) Were any aspects or features of the design (as illustrated in the drawing (s)) or described in the specification dictated or otherwise provided by a supplier? 4) If another entity or supplier contributed, or was involved in any way with the subject part/design/drawing/spec do we have terms in place that convey ownership in the design/drawings/specs and/or provide make and have made license rights? If the answer to any question in 1-3 is “yes” AND the answer to question 4 is “no”, then STOP. We cannot move or approve the drawings/design for quote without further IP Legal review and until all non-TGI information has been removed from all drawings/specs/etc. TGI RFQ policy must be followed.