## Form SCMP 7.5 b Rev B
SCMP Form 7.5 (b) Preliminary Risk Assessment - Complete prior to approval as part of developing the work transfer project strategy
Considerations Applicable to all Work Transfers- Any non-addressable item must be moved to Project Risk Assessment
Number | Potential New Source(s) | Yes/No | TGI WT Potential Actions(s) | Base Acceptability | Comments
1 | Will the transition affect another Triumph Group Business Unit? |  | Review all active projects on the Cost Management Project Tracker to determine all projects associated with the chosen supplier and review full list with all affect site purchasing leads, work transfer leads and supplier development leads to assess any constraints associated with additional work transfers | Confirmation that there are no constraints to adding a new work transfer to the chosen supplier |  | "yes","Confirm via Cost Management Project Tracker if selected supplier is on any other active projects or if the transition will impact existing supplier relationship."
2 | Is the capability to produce the part(s) within the suppliers capabilities? |  | If deemed necessary by the Engineering member of the sourcing/work transfer project team, the supplier may be assessed to demonstrate the specific capability to produce the specifc nominated parts | Confirmation from the Engineering team that the supplier is capable |  | "yes","Confirm if a validated SCMP 3.3 is in existance, if not schedule with Supplier Development to perform an SCMP 3.3.
3 | Do the supplier(s) have the capacity available to accommodate transfer? |  | Project Team to request that the Supplier Development team completes a supplier capacity study to demonstrate there is available capacity | Work Transfer Lead to request capacity charts from the supplier and determine if available capacity is demonstrated |  | "no","Coordinate Capacity Study with sources."
4 | Do the sources have an existing contract with Triumph Group with acceptable terms and conditions or are they willing to enter into an agreement with Triumph Group on acceptable Terms & Conditions? |  |  |  |  | "no","Contact Supply Chain Management Contract Specialist to Verify when/if an agreement will be executed"
5 | Are the sub-tier suppliers to the current source critical to the process or part? |  | Determine with the site engineering team if any sub-tier suppliers are critical to the process and must be utilized by the chosed new top level part supplier. Determine with the site enginering team if there are any critical key capabilities that need to be demonstrated by sub-tier suppliers If necessary, request the supplier development team and /or the Engineering team completes a capability assessment of critical sub-tier suppliers | Confrm with the chosen supplier that they have fully assessed all sub-tier suppliers to confirm they will meet all necessary requirments |  | "yes","Verify sub-tier supplier management capabilities."
6 | Is the current source a Small-Disadvantaged, Woman-owned, or Veteran-owned Business? |  | Review with the site Small Business Liason Officer to confirm if the new supplier is a Small-Disadvantaged, Woman-owned, or Veteran-owned Business and if so, are there any updates required to the sites overall categorization | See Potential Actions for Base Acceptablility |  | "yes","Review with SBLO and/or Contracts team.
7 | Are there any offset / Industrialization requirements or contractual requirements that affect this transfer? |  |  |  |  | "yes","Review with Contracts team.
8 | Could the current source's performance affect this transition? |  | Confirm with the site purchasing, Enginnering and quality project team members that there are no product integrity, quality or delivery issues with the current supplier Ensure any risks to product availability are captured ion the Overlap Plan | Complete an Overlap Plan and present to the project team |  | "yes","Develop mitigation plan for poor performance to be reflected in overlap plan.
9 | Are there any EH&S factors to be considered as part of this work transfer (e.g. materials of concern, EHS controls at the new source, liability concerns)? |  |  |  |  | "yes","Formally address concerns with Triumph Group EHS.
9.1 | Does the detailed project plan include validation and qualification requirements? |  | Confirm with receiving supplier progress of detail project plan and plan for meeting qualification requirements
9.2 | Have the training requirements been identified and agreed to? |  | Confirm with receiving supplier training requirements exist and subsequently updated for purposes of this Work Transfer
9.5 | Raw Materials and Sub-tier Management |  | TGI WT Potential Actions(s) | Base Acceptability | Comments
10 | Is the raw material that is currently used available to the potential new sources? |  | For Castings and Forgings - confirm in the Overlap Plan that materials are available to the new supplier For Raw Materials, make new supplier aware of any Triumph favorable pricing within the supply base | See Potential Actions for Base Acceptablility |  | "no","Identify approved source for material and secure forecast to support the transfer."
11 | Does the current source provide a product containing exotic materials (difficult to obtain, or needs to be procured in large volumes) or proprietary material (patented or controlled by a single manufacturer)? |  | Work with site Engineering and Supply Chain to determine specification and availability of materials | See Potential Actions for Base Acceptablility |  | "yes","Identify raw material requirements, long lead time items and bridge planning & special qualification testing requirements.
12 | Does the raw material for the potential new sources require an export license? |  | Confirm matarial designation with Site Export Control and determine who would need to establish an exprt licence | Definaition of export staus of material |  | "yes","Obtain export license."
12.5 | Product |  | TGI WT Potential Actions(s) | Base Acceptability | Comments
13 | Does the manufacture of the part have any processes or assembly methods that are Triumph Group and/or customer controlled. |  | Work with site Engineering to determine if there are any processes that are controlled by either Triumph or the customer | See Potential Actions for Base Acceptablility |  | "yes","Provide training/documents to supplier/obtain Customer approvals as required.
14 | Are there any customer requirements / Flow Downs that must be provided to the potential new sources? |  | Work with Contracts to determine if there are any customer requirements and/or flowdown required for the potential new sources | See Potential Actions for Base Acceptablility |  | "yes","Ensure Customer requirements hav been identified and will be part of the quote as applicable. Re: Customer Compliance Matrix
15 | Are there engineering or quality documents in place that supplement the drawing pack? (permits, concessions, deviation requests, in process ECNs, rework drawings, customer assertions) |  | Work with site Engineering and site Quality to determine if any additional documentation is required to supplement the drawing pack | See Potential Actions for Base Acceptablility |  | "yes","Ensure the drawing pack can stand on its own. Consider video or operator/routing interviews, auditing work instructions against actual process."
16 | Will the change of source of supply require requalification of the part or end-assembly? |  | Confirm with site Engineering if any change in the source of supply will require re-qualification of the part or the end-assembly | See Potential Actions for Base Acceptablility |  | "yes","Review & plan for requalification requirements. Create and approve qualification plan.
17 | Does the part have specific FAA, EASA, or DOD certification requirements that will require certification of the new supplier or TGI manufacturing facility? |  | Work wit hthe site Contracts and Compliance team to determine if there are any certification requirements for any new potential suppliers | See Potential Actions for Base Acceptablility |  | "yes","Review & plan for qualification requirements for new supplier / manufacturing facility. Ensure all types of manufacturing processes (OEM, PMA, DER) are mapped to identify and supplement any gaps
18 | Will the move of this product require any language translation of documentation (e.g. specs, drawings, work instructions) |  | Confirm if any potential suppliers will require language translation for the drawing pack | See Potential Actions for Base Acceptablility |  | "yes","Establish plan for language conversion and validation."
19 | Will the move of this product require any measurement conversions (e.g. english to metric) |  | Confirm if any potential suppliers will require measurement conversions | See Potential Actions for Base Acceptablility |  | "yes","Establish plan for measurement conversion and validation."
19.5 | Tooling & Equipment |  | TGI WT Potential Actions(s) | Base Acceptability | Comments
20 | Is there any Triumph Group owned tooling, test and/or manufacturing equipment involved in transfer? |  | Confirm if Triumph has tooling or test equipment that may be involved in the transfer | See Potential Actions for Base Acceptablility |  | "yes","Work with BD to Review Contract. Determine financial impact & CapEx req'ts. Review tooling condition and perform tooling validation (ie last article, laser inspection of the tool or internal review of productions parts). Address expor requirements
20.1 | Does the detailed project plan address tooling transfer or new tooling lead-times?
21 | Is there any Customer owned tooling, test and/or manufacturing equipment involved in transfer? |  | Confirm if the customer has tooling or test equipment that may be involved in the transfer | See Potential Actions for Base Acceptablility |  | "yes","Work with BD to Review Contract. Determine financial impact & CapEx req'ts. Review tooling condition and perform tooling validation (ie last article, laser inspection of the tool or internal review of productions parts). Address expor requirements
23 | Does the current source have source-owned tooling, test and/or manufacturing equipment? |  | Confirm if the current supplier (internal or external) has tooling or test equipmentthat may be involved in the transfer | See Potential Actions for Base Acceptablility |  | "yes","Work with BD to Review Contract. Determine financial impact & CapEx req'ts. Review tooling condition and perform tooling validation (ie last article, laser inspection of the tool or internal review of productions parts). Address expor requirements
23.5 | Resources |  | TGI WT Potential Actions(s) | Base Acceptability | Comments
24 | Is a communication plan required? |  | Confirm with Site Program Office the needs of the customer |  |  | "yes","Establish communication plan as required with internal and external stakeholders including internal Customers.
25 | Have the preliminary personnel requirements/team membership been established for this project? |  | Confirm with receiving supplier allocated resources to this effort |  |  | "no","Determine preliminary, dedicated personnel requirements & staffing plan including functional SME's.