## Form SCMP 7.5 b Rev E
SCMP Form 7.5 (b) Preliminary Risk Assessment - Complete prior to approval as part of developing the work transfer project
Considerations Applicable to all Work Transfers
Number | Potential New Source(s) | Yes/No | Triumph WT Potential Actions(s) | Base Acceptability | Comments
1 | Is the capability to produce the part(s) within the suppliers capabilities? | Answer | If deemed necessary by the Engineering member of the sourcing/work transfer project team, the supplier may be assessed to demonstrate the specific capability to produce the specific nominated parts | Confirmation from the Engineering team that the supplier is capable
2 | Do the supplier(s) have the capacity available to accommodate transfer? | Answer | If necessary, Project Team to request that the Supplier Development team completes a supplier capacity study to demonstrate there is available capacity | Work Transfer Lead to request capacity charts from the supplier and determine if available capacity is demonstrated
3 | Are the sub-tier suppliers to the current source critical to the process or part? | Answer | Determine with the site engineering team if any sub-tier suppliers are critical to the process and must be utilized by the chosen new top level part supplier. Determine with the site engineering team if there are any critical key capabilities that need to be demonstrated by sub-tier suppliers If necessary, request the supplier development team and /or the Engineering team completes a capability assessment of critical sub-tier suppliers | Confirm all potential suppliers have fully assessed all sub-tier suppliers to confirm they will meet all necessary requirements
4 | Could the current source's performance affect this transition? | Answer | Confirm with the site purchasing, Engineering and quality project team members that there are no product integrity, quality or delivery issues with the current supplier | Capture any issues in SCMP 7.5 (f) for inclusion in Overlap Plan
| Raw Materials and Sub-tier Management |  | Triumph WT Potential Actions(s) | Base Acceptability | Comments
5 | Is the raw material that is currently used available to the potential new sources? | Answer | For Castings and Forgings - confirm in the Overlap Plan that materials are available to the new supplier For Raw Materials, make new supplier aware of any Triumph favorable pricing within the supply base | See Potential Actions for Base Acceptability
6 | Does the current source provide a product containing exotic materials (difficult to obtain, or needs to be procured in large volumes) or proprietary material (patented or controlled by a single manufacturer)? | Answer | Work with site Engineering and Supply Chain to determine specification and availability of materials | See Potential Actions for Base Acceptability
7 | Does the raw material for the potential new sources require an export license? | Answer | Confirm material designation with Site Export Control and determine who would need to establish an export license | See Potential Actions for Base Acceptability
| Product |  | Triumph WT Potential Actions(s) | Base Acceptability | Comments
8 | Does the manufacture of the part have any processes, assembly methods and/or tooling that are Triumph Group and/or customer controlled. | Answer | Work with site Engineering to determine if there are any processes that are controlled by either Triumph or the customer (ex - Pre assembly FAI requirement) | See Potential Actions for Base Acceptability
9 | Confirm any non-standard customer requirements / flow downs were provided to the new source at RFQ and new source will comply? | Answer | Confirm with Sourcing Lead or with Contracts to determine if there are any customer requirements and/or flow down required for the potential new sources(See Comment for Examples) | See Potential Actions for Base Acceptability
10 | Are there engineering or quality documents in place that supplement the drawing pack? (permits, concessions, deviation requests, in process ECNs, rework drawings, customer assertions) | Answer | Work with site Engineering and site Quality to determine if any additional documentation is required to supplement the drawing pack | See Potential Actions for Base Acceptability
11 | Will the change of source of supply require requalification of the part or end-assembly? | Answer | Confirm with site Engineering if any change in the source of supply will require re-qualification of the part or the end-assembly | See Potential Actions for Base Acceptability
12 | Does the part have specific FAA, EASA, or DOD certification requirements that will require certification of the new supplier or TGI manufacturing facility? | Answer | Work with the site Contracts and Compliance team to determine if there are any certification requirements for any new potential suppliers | See Potential Actions for Base Acceptability
13 | Will the move of this product require any language translation of documentation (e.g. specs, drawings, work instructions) | Answer | Confirm if any potential suppliers will require language translation for the drawing pack | See Potential Actions for Base Acceptability
14 | Will the move of this product require any measurement conversions (e.g. English to metric) | Answer | Confirm if any potential suppliers will require measurement conversions | See Potential Actions for Base Acceptability
| Tooling & Equipment |  | Triumph WT Potential Actions(s) | Base Acceptability | Comments
15 | Does the current source have source-owned tooling, test and/or manufacturing equipment? | Answer | Confirm if the current supplier (internal or external) has tooling or test equipment that may be involved in the transfer | See Potential Actions for Base Acceptability
Yes
No
Answer
Note on D15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Examples include APQP; AS9117, PPAP, etc.