## 7.5(c) Project Risk Assessment
SCMP Form 7.5 (c), WT Project Risk Assessment
Source(s) | Yes / No | Suggested Actions | Specific Action | Comments
Is specialized training required to produce the part? | Yes | Coordinate training, as required.
Does the future source have an approved Designated Quality Representative (DQR) /Source Delegation Authority? | No | Develop a plan for obtaining source delegation, and for identification, training and implementation of DQR if applicable.
Has the new source considered any I&R requirements if applicable? | No | Source to validate drawing per Interchangeable & Replaceable requirement.
Has the new source reviewed all chemicals required to build the product to assure they are in compliance with local / state and government laws? | No | Ensure new source has list of chemical requirements and demonstrates knowledge regulatory requirements.
If required, has the supplier demostrated Production Rate Readiness? | No | Complete a Production Rate Readiness Assessment.
Has the new source reviewed the tracking requirements on product transfer such as utilizing the TGI Work Transfer Process and Tools? | No | Train and prvide standard work documentation.
Has the new source demonstrated the capability to meet rate readiness? | No | If required, Complete rate readiness capacity assessment and implement actions defined.
Raw Materials and Sub-tier Management | Yes / No | Suggested Actions | Specific Action | Comments
Has the new source considered raw material lead time impact to prevent disruption and support demand? | No | Review data with new source.
Product | Yes / No | Suggested Actions | Specific Action | Comments
Have you determined the exact configuration of the parts you have been receiving from the current source, that they meet the Engineering requirements (i.e. drawing & specs), and that the drawings and specifications are accurate, adequate and current (Techical Requirements Review)? | No | Perform Current Article Inspection (CAI) or equivalent. Engineering Review of drawing packs for issues (e.g. obsolete specs, dimensional ambiguity, errors) and provide data & Sample pieces to new source for their inspection upon Completion.
Do current process/manufacturing instructions need to be retrieved and reviewed? | Yes | Review documents and processes and if applicable, include as part of the knowledge transfer to new source. Document any un-documented processes or processes outside of system.
Has an inventory provisioning (residual, obsolete, active) and buffer stock plan (Line of Balance) been developed, if applicable? | No | Complete 7.5(d) overlap/ buffer stock plan.
Does the Triumph Group facility that will receive the future source parts for use have the ability to physically segregate transition inventory? | No | Develop plan to ensure no co-mingling of product until New source parts fully approved.
Has a detailed transportation & packaging plan with new supplier/ facility been established? (i.e. special crating, ESS considerations, specialized treatments, preferred carriers) | No | Establish transportation and packaging requirements.
Does the product or fabrication method require a Special Process? | Yes | Ensure the required process has approproriate approval or actions are established for approval.
Has an inspection plan been established with the new supplier? | No | Review supplier inspection plan or create an inspection plan with the supplier, as required.
Are there QNs and CAs from current source that should be shared with new source? (existing source intellectual property must be taken into consideration) | Yes | Review the QNs and CA's with new supplier that could impact manufacturability.
Is a Fit Check (Form, Fit, Function) at the end-item level, required? | Yes | Establish criteria and perform fit check and review with SME.
Tooling & Equipment | Yes / No | Suggested Actions | Specific Action | Comments
Do any of the existing tools need to be modified to support transfer? | Yes | Coordinate Pricing for Tool Modification with supplier or alternate source and obtain approvals.
Resources | Yes / No | Suggested Actions | Specific Action | Comments
Have the Specific Project success criteria been established and agreed by stakeholders? | No | Establish Success criteria and and agree with stakeholders
Aftermarket/Maintenance Repair & Overhaul | Yes / No | Suggested Actions | Specific Action | Comments
Will the on-going Audit Schedule be affected (e.g. flight safety audits)? | Yes | Review and update Audit Schedule as required.
Will the work transfer affect Direct Ship Authority letters? | Yes | Review and request revision if necessary to any current Direct Ship Authority letters.
Will Repair Station Manual(s) require revision to include the new work scope? | Yes | Initiate update(s) to Repair Station Manual(s) as required.
Is any tool equivalency required for the work transfer? | Yes | Submit and substantiate tool equivalency through Engineering
Yes
No
N/A