## 7.5c update
SCMP Form 7.5 (c), WT Project Risk Assessment
Number | Source(s) | Yes/No | TGI WT Potential Actions(s) | Base Acceptability | Comments
0 | Process |  | TGI WT Potential Actions(s) | Base Acceptability | Comments
1 | Is specialized training required to produce the part? |  | Bring supplier and site engineers together to review supplier route cards and manufacturing methods to determine if any specialized training is required | Obtain copy of suppliers route card and review internally with site engineering |  | "yes","Coordinate training, as required.
2 | Does the future source have an approved Designated Quality Representative (DQR) /Source Delegation Authority? |  | Determine if DRQ is required (and if necessary added to existing approval list) | Determine if DQR is required |  | "no","Develop a plan for obtaining source delegation, and for identification, training and implementation of DQR if applicable.
3 | Has the new source considered any I&R requirements if applicable? |  |  |  |  | no","Source to validate drawing per Interchangeable & Replaceable requirement.
4 | Has the new source reviewed all chemicals required to build the product to assure they are in compliance with local / state and government laws? |  | Review list of all chemicals to be used in the manufacture of the product and review OSHA documents to determine compliance with all Local and State laws | Receive written confirmation that all Local/State laws will be observed |  | "no","Ensure new source has list of chemical requirements and demonstrates knowledge regulatory requirements.
5 | If required, has the supplier demostrated Production Rate Readiness? |  |  |  |  | "no","Complete a Production Rate Readiness Assessment.
6 | Has the new source reviewed the tracking requirements on product transfer such as utilizing the TGI Work Transfer Process and Tools? |  | Confirm that in person or virtual training has been completed for all work transfer supplier requirements | See Potential Actions for Base Acceptability |  | no","Train and prvide standard work documentation
7 | Has the new source demonstrated the capability to meet rate readiness? |  | Review SCMP 3.3 |  |  | no","If required, Complete rate readiness capacity assessment and implement actions defined.
8 | Have the documentation and requirments for the receiving organization been clearly identified?
9 | Has the pre-move Knowledge Transfer been completed?
10 | Is the capacity at the receiving organization still confirmed as available for this transfer (all functions)?
11 | Have all Last Article Inspection(s) (LAIs) been completed?
12 | Is the work station documentation in place and correct?
13 | Has an MPR been done at the receiving organization?
14 | Has a PRR review been done to review the stage 4 deliverables including all qualification testing?
15 | Has capacity been verified?
16 | Has the customer approved the transfer of work, if required?
17 | Has the supply prepared a plan to reflect ability to meet future production rate?
18 | Raw Materials and Sub-tier Management |  | TGI WT Potential Actions(s) | Base Acceptability | Comments
19 | Has the new source considered raw material lead time impact to prevent disruption and support demand? Extract from 7.4a |  | Review route card and supplier Purchase Order to determine if Raw material availability meets schedule requirements | See Potential Actions for Base Acceptability |  | no","Review data with new source.
20 | Product |  | TGI WT Potential Actions(s) | Base Acceptability | Comments
21 | Have you (Qual/Eng) determined the exact configuration of the parts you have been receiving from the current source, that they meet the Engineering requirements (i.e. drawing & specs), and that the drawings and specifications are accurate, adequate and current (Techical Requirements Review)? |  |  |  |  | "no","Perform Current Article Inspection (CAI) or equivalent. Engineering Review of drawing packs for issues (e.g. obsolete specs, dimensional ambiguity, errors) and provide data & Sample pieces to new suource for their inspection upon completion
22 | Do current process/manufacturing instructions need to be retrieved and reviewed? |  |  |  |  | yes","Review documents and processes and if applicable, include as part of the knowledge transfer to new source. Document any un-documented processes or processes outside of system
23 | Has an Overlap Plan SCMP 7.5 (e) been completed |  | Complete a full Overlap Plan | Confirm the site does not require an Overlap Plan
24 | Does the Triumph Group facility that will receive the future source parts for use have the ability to physically segregate transition inventory? |  | Confirm the Triumph site has an IT and physical methods to segrigate transition inventory from new supplier | Confirm Triumph site has a physical method of transition stock segrigation |  | no","Develop plan to ensure no co-mingling of product until New source parts fully approved.
25 | Has a detailed transportation & packaging plan with new supplier/ facility been established? (i.e. special crating, ESS considerations, specialized treatments, preferred carriers) |  | Confirm with the Triumph site any specific transportation and packaging requirements and confirm compliance with transition supplier | See Potential Actions for Base Acceptability |  | no","Establish transportation and packaging requirements
26 | Does the product or fabrication method require a Special Process? |  | Confirm techincal and customer requirements for ALL special processes (whether performed in house at new supplier or sub-contracted) and note where each special process is being completed on the FAFP (including lead-times). If necessary, complete audit of all special process sources utilized | Confirm supplier will be in compliance with all special process requiremnts and that all suppliers are on their ASL |  | yes","Ensure the required process has approproriate approval or actions are established for approval."
27 | Has an inspection plan been established with the new supplier? |  | Review the inspection plan with internal Triumph site quality and engineering | See Potential Actions for Base Acceptability |  | no","Review supplier inspection plan or create an inspection plan with the supplier, as required.
28 | Are there QNs and CAs from current source that should be shared with new source? (existing source intellectual property must be taken into consideration) |  | Review data with work transfer project team and share (if necessary) with new supplier | See Potential Actions for Base Acceptability |  | yes","Review the QNs and CA's with new supplier that could impact manufacturability."
29 | Is a Fit Check (Form, Fit, Function) at the end-item level, required? |  | Confirm with Triumph site quality and engineering | See Potential Actions for Base Acceptability |  | yes","Establish criteria and perform fit check and review with SME.
30 | Has material handling, packaging, labeling and part marking been approved?
31 | Has PPAP (if required) and customer specific requirements been completed?
32 | Has a source inspection program been developed for the verification of the product from the receiving organization, if required?
33 | Tooling & Equipment |  | TGI WT Potential Actions(s) | Base Acceptability | Comments
34 | Do any of the existing tools need to be modified to support transfer? |  | If tooling is to be reused, arrange a joint review between the supplier and the site engineering team to confirm and approve the program of modifictation | Send the proposed tooling modifications to the site engineering team for review and approval |  | yes","Coordinate Pricing for Tool Modification with supplier or alternate source and obtain approvals
35 | Resources |  | TGI WT Potential Actions(s) | Base Acceptability | Comments
36 | Have the Specific Project success criteria been established and agreed by stakeholders? |  |  |  |  | no","Establish Success criteria and and agree with stakeholders
37 | Aftermarket/Maintenance Repair & Overhaul |  | TGI WT Potential Actions(s) | Base Acceptability | Comments
38 | Will the on-going Audit Schedule be affected (e.g. flight safety audits)? |  | Confirm if the chosen supplier is already on the site list of audits (in person or desk top). If supplier is not on the standard audit schedule, confirm with site quality that the supplier is added to the schedule | See Potential Actions for Base Acceptability |  | yes","Review and update Audit Schedule as required.
39 | Will the work transfer affect Direct Ship Authority letters? |  | Confirm if the parts for transfer are on any existing Direct Ship Authority letters, and if so confirm that the new supplier will be included in any Direct Ship authorizations | See Potential Actions for Base Acceptability |  | yes","Review and request revision if necessary to any current Direct Ship Authority letters.
40 | Will Repair Station Manual(s) require revision to include the new work scope? |  | Confirm if any repair station manuals will need to be updated by confirming with site engineering | See Potential Actions for Base Acceptability |  | yes","Initiate update(s) to Repair Station Manual(s) as required.
41 | Is any tool equivalency required for the work transfer? |  |  |  |  | yes","Submit and substantiate tool equivalency through Engineering