## Form SCMP 7.5 c Rev C
SCMP Form 7.5 (c), WT Project Risk Assessment
Considerations Applicable to all Work Transfers
| Process |  | Triumph WT Potential Actions(s) | Base Acceptability | Comments
1 | Is specialized training required to produce the part? | Answer | Bring supplier and site engineers together to review supplier route cards and manufacturing methods to determine if any specialized training is required | Obtain copy of suppliers route card and review internally with site engineering
2 | Does the new source have an approved Designated Quality Representative (DQR) /Source Delegation Authority? | Answer | Determine if DRQ is required (and if necessary added to existing approval list) | Determine if DQR is required and to be applied to the new products
3 | Has the new source reviewed all chemicals required to build the product to assure they are in compliance with local / state and government laws? | Answer | Review list of all chemicals to be used in the manufacture of the product and review OSHA documents to determine compliance with all Local and State laws | Receive written confirmation that all Local/State laws will be observed
4 | Has the new source reviewed the tracking requirements on product transfer such as utilizing the Triumph Work Transfer Process and Tools? | Answer | Confirm that in person or virtual training has been completed for all work transfer supplier requirements | See Potential Actions for Base Acceptability
5 | Has the new source demonstrated the capability & capacity to meet rate following award of new business? | Answer | Review Supplier Part Plan to meet rate and capture on SCMP 7.5 (d) if necessary | See Potential Actions for Base Acceptability
6 | Has the pre-move Knowledge Transfer been completed? | Answer | Confirm supplier need to have Technical Interchange Meeting (TIM) to support mfg | See Potential Actions for Base Acceptability
7 | Is the capacity at the receiving organization still confirmed as available for this transfer (all functions)? | Answer | Confirm FAFP Part integration plan with all internal functions | See Potential Actions for Base Acceptability
8 | Has Triumph received customer approval and/or notification verification for the transfer of work? | Answer | Confirm all approvals are in place. If approval and/or notification has not been received WT should escalate to responsible parties | See Potential Actions for Base Acceptability | Triumph Action
| Product |  | Triumph WT Potential Actions(s) | Base Acceptability | Comments
9 | Has an Overlap Plan SCMP 7.5 (e) been completed | Answer | Complete a full Overlap Plan | Confirm the site does not require an Overlap Plan | Triumph Action
10 | Does the Triumph facility that will receive the future source parts for use have the ability to physically segregate transition inventory? | Answer | Confirm the Triumph site has an IT and physical methods to segrigate transition inventory from new supplier | Confirm Triumph site has a physical method of transition stock segrigation | Triumph Action
11 | Has a detailed transportation & packaging plan with new supplier/ facility been established? (i.e. special crating, ESS considerations, specialized treatments, preferred carriers) | Answer | Confirm with the Triumph site any specific transportation and packaging requirements and confirm compliance with transition supplier | See Potential Actions for Base Acceptability | Triumph Action
12 | Does the product or fabrication method require a Special Process? | Answer | Confirm techincal and customer requirements for ALL special processes (whether performed in house at new supplier or sub-contracted) and note where each special process is being completed on the FAFP (including lead-times). If necessary, complete audit of all special process sources utilized | Confirm supplier will be in compliance with all special process requiremnts and that all suppliers are on their ASL
13 | Has an inspection plan been established with the new supplier? | Answer | Review the inspection plan with internal Triumph site quality and engineering | See Potential Actions for Base Acceptability
14 | Are there QNs and CAs from current source that should be shared with new source? (existing source intellectual property must be taken into consideration) | Answer | Review data with work transfer project team and share (if necessary) with new supplier | See Potential Actions for Base Acceptability | Triumph Action
15 | Is a Fit Check (Form, Fit, Function) at the end-item level, required? | Answer | Confirm with Triumph site quality and engineering | See Potential Actions for Base Acceptability | Triumph Action
16 | Has material handling, packaging, labeling and part marking been approved? | Answer | Confirm approval | See Potential Actions for Base Acceptability
17 | Has a source inspection program been developed for the verification of the product from the receiving organization, if required? | Answer | Confirm Source Approval in place | See Potential Actions for Base Acceptability
| Tooling & Equipment |  | Triumph WT Potential Actions(s) | Base Acceptability | Comments
18 | Do any of the existing tools need to be modified to support transfer? | Answer | If tooling is to be reused, arrange a joint review between the supplier and the site engineering team to confirm and approve the program of modifictation | Send the proposed tooling modifications to the site engineering team for review and approval
| Resources |  | TGI WT Potential Actions(s) | Base Acceptability | Comments
19 | Have the Specific Project success criteria been established and agreed by stakeholders? | Answer | Determine success criteria | See Potential Actions for Base Acceptability
| Aftermarket/Maintenance Repair & Overhaul |  | TGI WT Potential Actions(s) | Base Acceptability | Comments
20 | Will the work transfer affect Direct Ship Authority letters? | Answer | Confirm if the parts for transfer are on any existing Direct Ship Authority letters, and if so confirm that the new supplier will be included in any Direct Ship authorizations | See Potential Actions for Base Acceptability | Triumph Action
21 | Will Repair Station Manual(s) require revision to include the new work scope? | Answer | Confirm if any repair station manuals will need to be updated by confirming with site engineering | See Potential Actions for Base Acceptability | Triumph Action
Yes
No
Answer