## New Source - SCMP 7.5 c Rev E
SCMP Form 7.5 (c), WT Project Risk Assessment
Considerations Applicable to all Work Transfers
| Process |  | Triumph WT Potential Actions(s) | Base Acceptability | Comments
1 | Has the new source identified or requested any specialized training required to produce the part? | Answer | Bring supplier and site engineers together to review supplier route cards and manufacturing methods to determine if any specialized training is required | Obtain copy of suppliers route card and review internally with site engineering
2 | Has the new source reviewed the Triumph First Article Flow Plan (FAFP) tracking requirements and/or supplemental customer work transfer forms. | Answer | Confirm that in person or virtual training has been completed for all work transfer supplier requirements | See Potential Actions for Base Acceptability
3 | Has the new source received any additional work from Triumph or other customers since the RFQ that would affect this transfer? | Answer | Review capacity from SSR if completed and determine if project can proceed forward. | See Potential Actions for Base Acceptability
4 | Has the new source reviewed any pre-move Knowledge Transfer material as supplied by Triumph? | Answer | Confirm supplier need to have Technical Interchange Meeting (TIM) to support mfg | See Potential Actions for Base Acceptability
| Product |  | Triumph WT Potential Actions(s) | Base Acceptability | Comments
5 | Does the product or fabrication method require a Special Process? | Answer | Confirm techincal and customer requirements for ALL special processes (whether performed in house at new supplier or sub-contracted) and note where each special process is being completed on the FAFP (including lead-times). If necessary, complete audit of all special process sources utilized | Confirm supplier will be in compliance with all special process requiremnts and that all suppliers are on their ASL
6 | Has the new source identified areas of concern or methods of inspection that should be reveiwed or dicussed? | Answer | Review the inspection plan with internal Triumph site quality and engineering | See Potential Actions for Base Acceptability
Yes
No
Answer

## Triumph - SCMP 7.5 c Rev E
SCMP Form 7.5 (c), WT Project Risk Assessment
Considerations Applicable to all Work Transfers
| Process |  | Triumph WT Potential Actions(s) | Base Acceptability | Comments
1 | Has a detailed transportation & packaging plan with new supplier/ facility been established? (i.e. special crating, ESS considerations, specialized treatments, preferred carriers) | Answer | Confirm with the Triumph site any specific transportation and packaging requirements and confirm compliance with transition supplier | See Potential Actions for Base Acceptability | Triumph Action
2 | Has Triumph received customer approval and/or notification verification for the transfer of work? | Answer | Confirm all approvals are in place. If approval and/or notification has not been received WT should escalate to responsible parties | See Potential Actions for Base Acceptability | Triumph Action
3 | Has an Overlap Plan SCMP 7.5 (e) been completed | Answer | Complete a full Overlap Plan | Confirm the site does not require an Overlap Plan | Triumph Action
4 | Does the Triumph facility that will receive the future source parts for use have the ability to physically segregate transition inventory? | Answer | Confirm the Triumph site has an IT and physical methods to segregate transition inventory from new supplier | Confirm Triumph site has a physical method of transition stock segregation | Triumph Action
5 | Are there QNs and CAs from current source that should be shared with new source? (existing source intellectual property must be taken into consideration) | Answer | Review data with work transfer project team and share (if necessary) with new supplier | See Potential Actions for Base Acceptability | Triumph Action
6 | Is a Fit Check (Form, Fit, Function) at the end-item level, required? | Answer | Confirm with Triumph site quality and engineering | See Potential Actions for Base Acceptability | Triumph Action