## First Article Flow Plan
First Article Flow Plan | [77 empty] | Holidays Excluded
Receiving Supplier: |  |  |  | TGI Companies Transitioning Parts:
Transition Package: |  |  |  | TGI Transition Project Manager:
Last Updated by: |  | Name of Person |  | TGI Buyer:
Date of Last Update: |  | Date of Update
Today's Date |  | 2025-02-14
CMPT WT Project # |  | ABC
|  |  |  | Supplier Lead Time Blow-Back (M-Days) | [6 empty] | 0 |  |  | 30 |  |  | 0 |  |  | 10 |  |  | 10 |  |  | 5 |  |  | 0 |  |  | 10 |  |  | 2 |  |  | 3 |  |  | 2 |  |  | 15 |  |  | 0 |  |  | 2 |  |  | 4 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 4 |  |  | 3 |  |  | 2 | [6 empty] | 43976
[5 empty] | % COMPLETE |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0% |  |  | 0%
[5 empty] | COMPLETE |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[5 empty] | BALANCE DUE |  |  | 20 |  |  | 40 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20 |  |  | 20
Item Number | Assembly/Part Number | Dash Rolls | Part Description | Section (Next Higher Assy) | Program | Site | # Per Ship | PO Placed | PO | PO Item | Engr Data Received |  |  | Material Ordered |  |  | Material DOD |  |  | NC Tool Design |  |  | NC Program |  |  | Planning |  |  | Issue Material & Realease WO |  |  | Tool FAB |  |  | Machine Start/Rough |  |  | Machine Finish |  |  | Inspect |  |  | Outside Processing Out |  |  | Outside Processing Rcv |  |  | ID |  |  | Detail Net-Inspect Submit |  |  | Detail FAI |  |  | Assembly Start |  |  | Assembly Finish |  |  | Assy Net-Inspect Submit |  |  | Assembly FAI |  |  | PKG/Ship |  |  | PO On Dock Date |  |  | Comments
[11 empty] | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Revised Plan | Actual | Plan | Commit Date | Actual
1 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01 | 2023-01-10
2 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
3 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
4 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
5 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
6 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
7 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
8 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
9 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
10 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
11 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
12 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
13 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
14 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
15 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
16 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
17 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
18 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
19 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
20 | [10 empty] | 2020-12-31 |  |  | 2020-12-31 |  |  | 2021-02-11 |  |  | 2021-02-11 |  |  | 2021-02-25 |  |  | 2021-03-11 |  |  | 2021-03-18 |  |  | 2021-03-18 |  |  | 2021-04-01 |  |  | 2021-04-05 |  |  | 2021-04-08 |  |  | 2021-04-12 |  |  | 2021-05-03 |  |  | 2021-05-03 |  |  | 2021-05-05 |  |  | 2021-05-11 |  |  | 2021-05-13 |  |  | 2021-05-17 |  |  | 2021-05-19 |  |  | 2021-05-25 |  |  | 2021-05-28 |  |  | 2021-06-01
Formulas:
Engr Data Received = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Material Ordered],WORKDAY([Material Ordered],-L9,CI2:CI19))
Material Ordered = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Material DOD],WORKDAY([Material DOD],-O9,CI2:CI19))
Material DOD = IF(ISNUMBER(SEARCH("N/A",[Actual])),[NC Tool Design],WORKDAY([NC Tool Design],-R9,CI2:CI19))
NC Tool Design = IF(ISNUMBER(SEARCH("N/A",[Actual])),[NC Program],WORKDAY([NC Program],-U9,CI2:CI19))
NC Program = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Planning],WORKDAY([Planning],-X9,CI2:CI19))
Planning = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Issue Material & Realease WO],WORKDAY([Issue Material & Realease WO],-AA9,CI2:CI19))
Issue Material & Realease WO = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Tool FAB],WORKDAY([Tool FAB],-AD9,CI2:CI19))
Tool FAB = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Machine Start/Rough],WORKDAY([Machine Start/Rough],-AG9,CI2:CI19))
Machine Start/Rough = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Machine Finish],WORKDAY([Machine Finish],-AJ9,CI2:CI19))
Machine Finish = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Inspect],WORKDAY([Inspect],-AM9,CI2:CI19))
Inspect = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Outside Processing Out],WORKDAY([Outside Processing Out],-AP9,CI2:CI19))
Outside Processing Out = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Outside Processing Rcv],WORKDAY([Outside Processing Rcv],-AS9,CI2:CI19))
Outside Processing Rcv = IF(ISNUMBER(SEARCH("N/A",[Actual])),[ID],WORKDAY([ID],-AV9,CI2:CI19))
ID = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Detail Net-Inspect Submit],WORKDAY([Detail Net-Inspect Submit],-AY9,CI2:CI19))
Detail Net-Inspect Submit = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Detail FAI],WORKDAY([Detail FAI],-BB9,CI2:CI19))
Detail FAI = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Assembly Start],WORKDAY([Assembly Start],-BE9,CI2:CI19))
Assembly Start = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Assembly Finish],WORKDAY([Assembly Finish],-BH9,CI2:CI19))
Assembly Finish = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Assy Net-Inspect Submit],WORKDAY([Assy Net-Inspect Submit],-BK9,CI2:CI19))
Assy Net-Inspect Submit = IF(ISNUMBER(SEARCH("N/A",[Actual])),[Assembly FAI],WORKDAY([Assembly FAI],-BN9,CI2:CI19))
Assembly FAI = IF(ISNUMBER(SEARCH("N/A",[Actual])),[PKG/Ship],WORKDAY([PKG/Ship],-BQ9,CI2:CI19))
PKG/Ship = IF(ISNUMBER(SEARCH("N/A",[Actual])),[PO On Dock Date],WORKDAY([PO On Dock Date],-BT9,CI2:CI19))

## Old FAPF Plan (hidden)
|  | Person | [5 empty] | TA-VAD Team Members | [7 empty] | TS-KC Team Members | [12 empty] | TODAY = | 2025-02-14
| Last Updated by: | Jace Kline | [5 empty] | Project Lead: Joe Ragusa (972) 946-5422 | [7 empty] | Project Lead: Jace Kline (817) 529-6179
| Date: | 2025-02-14 | [5 empty] | Buyer: Brandy Gillingham (M), Monica Navarro (H), Drew Culton (S)
Tech Ops: As Needed
SQE: As Needed
Essner |  |  | 1) PO’s will be issued with a –FP suffix. 2) Parts will be delivered without -FP sufix. 3) Refer to TSSP for part identification. 4) Request correction if TSSP doesn't specivy part identification without -FP sufix.
Gray out if operation not required | [9 empty] | Lead time blow-back (M-Days) ---> | 1 | 1 | 10 | 7 | 7 | 3 | 0 | 10 | 10 | 2 | 2 | 10 | 15 | 3 | 0 | 0 |  | 3 | 2 | 7
| % COMPLETE | [6 empty] | 98.44% |  |  | 100% | 100% | 85.96% | 85.96% | 84.21% | 84.21% | 68.42% | 77.19% | 77.19% | 77.19% | 77.19% | 63.16% | 63.16% | 63.16% | 47.37% | 47.37% |  | 61.4% | 47.37% | 47.37%
| COMPLETE | [6 empty] | 63 |  |  | 57 | 57 | 49 | 49 | 48 | 48 | 39 | 44 | 44 | 44 | 44 | 36 | 36 | 36 | 27 | 27 |  | 35 | 27 | 27
| BALANCE DUE | [6 empty] | 1 |  |  | 0 | 0 | 8 | 8 | 9 | 9 | 18 | 13 | 13 | 13 | 13 | 21 | 21 | 21 | 30 | 30 |  | 22 | 30 | 30
Item Number | Part Number (PO Suffix -FP) | Dash Rolls | Part Description | Section (NHA) | Prog | Site | Qty Per Ship | PO Placed | PO | PO Item | Eng Data Received | Material | Tooling Design/Fab/Transfer | Planning | NC Program | Shear & Saw | Saw | Route/ Water Jet | Forming & Trimming | Deburr | Inspect | Heat Treat/ Age | Outside Process | Prime, Paint | Paint | Assembly | Assembly | FAI Inspect | Source Inspect | Ship Date | PO On-Dock Date | Lock Down PO "On Dock Date" | Comments | COMMENTS | Package (Ref) | Tool Status
1 | 148U3928-1 |  | STRINGER, REINFORCEMENT | 481-3-2190 | 747 | 1600 | 2 | Y | 4500051961 | 10 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | 2013-10-09 | 2013-10-09 |  | 2013-10-09 | 2013-10-14 | 2013-10-16 | 2013-10-25 | Yes | 148U3928-1 | Parts are in Final Q.A | (#3) LTA/0298/2013 | Tools at Essner
2 | 65B17373-20 |  | STRAP | 4230D/2-9070-8F | 747 | 1600 | 1 | Y | 4500052158 | 70 | C | C | C | C | C | C | C | C | C | C | C | 2013-09-06 | 2013-09-20 | 2013-10-11 | 2013-10-16 | 2013-10-16 |  | #NAME? | #NAME? | #NAME? | 2013-11-01 | Yes | 65B17373-20 | Parts are at Gamma for Heat Treat | (#9) LTA/0302/2013 | Tools at TAVAD shipping Dock
3 | 65B07491-47-01 |  | INTERCOSTAL, | 4655/9070-1 | 747 | 1300 | 1 | Y | 4500051430 | 60 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | #NAME? |  |  | C | #NAME? | #NAME? | 2013-11-01 | Yes | 65B07491-47-01 | Ready for Source/Net-inspect Approval | (#9) LTA/0302/2013 | Tools at TAVAD shipping Dock
4 | 65B07478-13 |  | STRAP | 4630R/9020-1 | 747 | 1300 | 1 | Y | 4500051430 | 50 | C | C | C | C | C | C | C | C | C | C | C | 2013-09-26 | 2013-09-20 | 2013-10-11 | 2013-10-16 | 2013-10-16 |  | #NAME? | #NAME? | #NAME? | 2013-11-01 | Yes | 65B07478-13 | Parts are at Gamma for Heat Treat | (#9) LTA/0302/2013 | Tools at TAVAD shipping Dock
5 | 65B06351-15-01 |  | ANGLE, | 4632L/7060-2 | 747 | 1300 | 1 | Y | 4500051430 | 30 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | #NAME? |  |  | C | #NAME? | #NAME? | 2013-11-01 | Yes | 65B06351-15-01 | Ready for Source/Net-inspect Approval | (#9) LTA/0302/2013 | Tools at TAVAD shipping Dock
6 | 65B26187-404 |  | SUPPORT ANGLE | 65B26187-410 | 747 | 1300 | 5 | Y | 4500051430 | 100 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | #NAME? |  |  | C | #NAME? | #NAME? | 2013-11-30 | Yes | #REF! | Ready for Source/Net-inspect Approval | (#9) LTA/0302/2013
7 | 65B26187-403 |  | SUPPORT ANGLE , | 65B26187-410 | 747 | 1300 | 5 | Y | 4500051430 | 90 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | #NAME? |  |  | C | #NAME? | #NAME? | 2013-11-30 | Yes | #REF! | Ready for Source/Net-inspect Approval | (#9) LTA/0302/2013
8 | 65B07491-48-01 |  | INTERCOSTAL, | 4640/9030-1 | 747 | 1300 | 1 | Y | 4500051430 | 70 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | #NAME? |  |  | C | #NAME? | #NAME? | 2013-11-30 | Yes | #REF! | Ready for Source/Net-inspect Approval | (#9) LTA/0302/2013
9 | 65B07174-433 |  | STIFFENER, | 4636/8070-1 | 747 | 1300 | 1 | Y | 4500051430 | 40 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | #NAME? |  |  | C | #NAME? | #NAME? | 2013-11-30 | Yes | #REF! | Ready for Source/Net-inspect Approval | (#9) LTA/0302/2013
10 | 65B04406-608 |  | WEB , | 65B04406-882-06 | 747 | 1800 | 1 | Y | 4500053392 | 10 | C | C | C | C | [8 empty] | #NAME? |  | #NAME? |  |  | #NAME? | #NAME? | #NAME? |  | Essner needs (1) FD | #REF! | MISSING TOOL 4881684-00/C00 FD - BACD2000-10 | (#9) LTA/0302/2013
12 | 185T4000-013-1000 |  | WEB, | 185T4000-183-533 | 767 Common | 1600 | 1 | Y | 4500052161 | 70 | C | C | C | C | C | C |  | C | C | C | C | 2013-10-02 | #NAME? | 2013-11-06 | #NAME? | 2013-11-11 |  | #NAME? | #NAME? | #NAME? | 2013-11-30 |  |  | Parts in Queue for Heat Treat in-house | (#9) LTA/0302/2013
13 | 185T4000-011-2000 |  | WEB, AFT T/B FIN | 185T4000-184-532 | 767 Common | 1600 | 1 | Y | 4500052161 | 60 | C | C | 2013-08-09 | 2013-08-14 | 2013-08-14 | 2013-08-23 | 2013-08-28 | 2013-08-28 | 2013-09-12 | 2013-09-26 | 2013-09-30 | 2013-10-02 | #NAME? | 2013-11-06 | #NAME? | 2013-11-11 |  | #NAME? | #NAME? | #NAME? | 2013-11-30 |  |  | Missing tools/Docs | (#9) LTA/0302/2013
14 | 185T4000-011-1000 |  | DOUBLER, FWD T/B FIN | 185T4000-183-533 | 767 Common | 1600 | 1 | Y | 4500052161 | 50 | C | C | 2013-08-09 | 2013-08-14 | 2013-08-14 | 2013-08-23 | 2013-08-28 | 2013-08-28 | 2013-09-12 | 2013-09-26 | 2013-09-30 | 2013-10-02 | #NAME? | 2013-11-06 | #NAME? | 2013-11-11 |  | #NAME? | #NAME? | #NAME? | 2013-11-30 |  |  | Missing tools/Docs | (#9) LTA/0302/2013
15 | 185T4000-009-1000 |  | WEB, | 185T4000-183-533 | 767 Common | 1600 | 1 | Y | 4500052161 | 40 | C | C | 2013-08-09 | 2013-08-14 | 2013-08-14 | 2013-08-23 | 2013-08-28 | 2013-08-28 | 2013-09-12 | 2013-09-26 | 2013-09-30 | 2013-10-02 | #NAME? | 2013-11-06 | #NAME? | 2013-11-11 |  | #NAME? | #NAME? | #NAME? | 2013-11-30 |  |  | Missing tools/Docs | (#9) LTA/0302/2013
16 | 185T4000-008-1000 |  | WEB, | 185T4000-184-532 | 767 Common | 1600 | 1 | Y | 4500052161 | 30 | C | C | 2013-08-09 | 2013-08-14 | 2013-08-14 | 2013-08-23 | 2013-08-28 | 2013-08-28 | 2013-09-12 | 2013-09-26 | 2013-09-30 | 2013-10-02 | #NAME? | 2013-11-06 | #NAME? | 2013-11-11 |  | #NAME? | #NAME? | #NAME? | 2013-11-30 |  |  | Missing tools/Docs | (#9) LTA/0302/2013
17 | 185T4000-007-1000 |  | WEB, | 185T4000-183-533 | 767 Common | 1600 | 1 | Y | 4500052161 | 20 | C | C | 2013-08-09 | 2013-08-14 | 2013-08-14 | 2013-08-23 | 2013-08-28 | 2013-08-28 | 2013-09-12 | 2013-09-26 | 2013-09-30 | 2013-10-02 | #NAME? | 2013-11-06 | #NAME? | 2013-11-11 |  | #NAME? | #NAME? | #NAME? | 2013-11-30 |  |  | Missing tools/Docs | (#9) LTA/0302/2013
18 | 174U9300-009-500 |  | SUPPORT,DORSAL FIN SEAL ASSY. | 174U9300-010-522 | 747 | 1600 | 2 | Y | 4500052158 | 50 | C | C | 2013-08-09 | 2013-08-14 | 2013-08-14 | 2013-08-23 | 2013-08-28 | 2013-08-28 | 2013-09-12 | 2013-09-26 | 2013-09-30 | 2013-10-02 | #NAME? | 2013-11-06 | #NAME? | 2013-11-11 |  | #NAME? | #NAME? | #NAME? | 2013-11-30 |  |  | Missing tools/Docs | (#9) LTA/0302/2013
19 | 173U3509-5-01 |  | WEB, RUDDER | 173U3509-1-01 | 747 | 1600 | 1 | Y | 4500052158 | 40 | C | C | 2013-08-09 | 2013-08-14 | 2013-08-14 | 2013-08-23 | 2013-08-28 | 2013-08-28 | 2013-09-12 | 2013-09-26 | 2013-09-30 | 2013-10-02 | #NAME? | 2013-11-06 | #NAME? | 2013-11-11 |  | #NAME? | #NAME? | #NAME? | 2013-11-30 |  |  | Missing tools/Docs | (#9) LTA/0302/2013
20 | 173U3507-8-01 |  | WEB, | 173U3507-1-01 | 747 | 1600 | 1 | Y | 4500052158 | 30 | C | C | 2013-08-09 | 2013-08-14 | 2013-08-14 | 2013-08-23 | 2013-08-28 | 2013-08-28 | 2013-09-12 | 2013-09-26 | 2013-09-30 | 2013-10-02 | #NAME? | 2013-11-06 | #NAME? | 2013-11-11 |  | #NAME? | #NAME? | #NAME? | 2013-11-30 |  |  | Missing tools/Docs | (#9) LTA/0302/2013
21 | 173U3502-12-01 |  | WEB, | 173U3502-11-01 | 747 | 1600 | 1 | Y | 4500052158 | 20 | C | C | C | C | C | C | 2013-08-28 | 2013-08-28 | 2013-09-12 | 2013-09-26 | 2013-09-30 | 2013-10-02 | 2013-10-16 | 2013-11-06 | 2013-11-11 | 2013-11-11 |  | 2013-11-11 | 2013-11-14 | 2013-11-18 | 2013-11-30 |  |  | Still missing tools | (#9) LTA/0302/2013
22 | 65B04693-601 |  | INNER SKIN | 2520-3-3005/PMC10 | 747 | 1800 | 1 | Y | 4500053392 | 30 | C | C | C | C | C | C | 2013-09-18 | 2013-09-18 | 2013-10-02 | 2013-10-16 | 2013-10-18 | 2013-10-22 | 2013-11-05 | 2013-11-26 | 2013-12-03 | 2013-12-03 |  | 2013-12-03 | 2013-12-06 | 2013-12-10 | 2013-12-19 | Yes | Yes- lock down date | Parts in Queue at Water jet | (#9) LTA/0302/2013
23 | 65B09684-8 |  | STRAP, | 4210L/9090-1 | 747 | 1300 | 4 | Y | 4500051430 | 80 | C | C | C | C | C | C | C | C | C | C | C | 2013-10-23 | 2013-11-06 | 2013-11-27 | 2013-12-04 | 2013-12-04 |  | 2013-12-04 | 2013-12-09 | 2013-12-11 | 2013-12-20 | Yes | Yes- lock down date | Parts are at Gamma for Heat Treat | (#9) LTA/0302/2013
24 | 65B07491-49 |  | INTERCOSTAL, FRAME | 4610D/3-9010-8F | 747 | 1600 | 1 | Y | 4500052158 | 60 | C | C | C | C | C | C |  | C | C | C | C | 2013-10-23 | 2013-11-06 | 2013-11-27 | 2013-12-04 | 2013-12-04 |  | 2013-12-04 | 2013-12-09 | 2013-12-11 | 2013-12-20 | Yes | Yes- lock down date | Parts in Queue for Heat Treat in-house | (#9) LTA/0302/2013
25 | 65B04718-601 |  | INNER SKIN | 6530-3-3005/PMC10 | 747 | 1800 | 1 | Y | 4500053392 | 50 | C | C | C | C | C | C | 2013-09-19 | 2013-09-19 | 2013-10-03 | 2013-10-17 | 2013-10-21 | 2013-10-23 | 2013-11-06 | 2013-11-27 | 2013-12-04 | 2013-12-04 |  | 2013-12-04 | 2013-12-09 | 2013-12-11 | 2013-12-20 | Yes | Yes- lock down date | Parts in Queue at Water jet | (#9) LTA/0302/2013
26 | 185T4000-013-2000 |  | WEB, | 185T4000-184-532 | 767 Common | 1600 | 1 | Y | 4500052161 | 80 | C | C | C | C | C | C |  | C | C | C | C | 2013-10-23 | 2013-11-06 | 2013-11-27 | 2013-12-04 | 2013-12-04 |  | 2013-12-04 | 2013-12-09 | 2013-12-11 | 2013-12-20 | Yes | Yes- lock down date | Parts in Queue for Heat Treat in-house | (#9) LTA/0302/2013
27 | 173U2018-024 |  | DOOR, | 173U2018-014-501 | 747 | 1600 | 2 | Y | 4500051961 | 40 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | #NAME? |  |  | C | #NAME? | #NAME? | 2013-12-20 | Yes | Yes- lock down date | Ready for Source/Net-inspect Approval | (#3) LTA/0298/2013
28 | 146U7251-7 |  | STABILIZATION, FRAME | 4610D/3-9010-8F | 747 | 1600 | 1 | Y | 4500052158 | 10 | C | C | C | C | C | C |  | C | C | C | C | 2013-10-23 | #NAME? | #NAME? | #NAME? | 2013-12-04 |  | #NAME? | #NAME? | #NAME? | 2013-12-20 | Yes | Yes- lock down date | Parts in Queue for Heat Treat in-house | (#9) LTA/0302/2013
29 | 146U5321-212 |  | ANGLE, | 4632R/7060-2 | 747 | 1300 | 1 | Y | 4500051430 | 10 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | #NAME? |  |  | C | #NAME? | #NAME? | 2013-12-20 | Yes | Yes- lock down date | Ready for Source/Net-inspect Approval | (#9) LTA/0302/2013
30 | 69B04657-1-01 |  | SHEAR PANEL, | 4631R/8040-1 | 747 | 1300 | 1 | Y | 4500051430 | 150 | C | C | C | C | C | C |  | C | C | C | C | 2013-10-23 | #NAME? | #NAME? | #NAME? | 2013-12-04 |  | #NAME? | #NAME? | #NAME? | 2013-12-20 | Yes | Yes- lock down date | Parts in Queue for Heat Treat in-house | (#9) LTA/0302/2013
31 | 185T4000-125-1000 |  | WEB, | 185T4000-184-532 | 767 Common | 1600 | 1 | Y | 4500052161 | 90 | C | C | C | C | C | C | 2013-11-15 | 2013-11-15 | 2013-12-03 | 2013-12-17 | 2013-12-19 | 2014-01-02 | #NAME? | #NAME? | #NAME? | 2014-02-12 |  | #NAME? | #NAME? | #NAME? | 2014-02-28 | Yes | Yes- lock down date | Parts in Queue at Water jet | (#9) LTA/0302/2013
11 | 65B04241-55 |  | CHANNEL | 65B04241-410 | 747 | 1300 | 1 | Y | 4500051430 | 20 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes | #REF! | Shipped Complete | (#9) LTA/0302/2013
32 | 180T3250-011 |  | RAIN GUTTER, | 180T3250-009 | 767 Common | 1600 | 6 | Y | 4500052161 | 10 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes | 180T3250-011 | Shipped Complete | (#9) LTA/0302/2013
33 | 100T1481-033 |  | TAPER FILLER, | 145T9999-2200-010 | 767 | 1800 | 1 | Y | 4500053417 | 70 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
34 | 100T1481-026 |  | FILLER, | 145T9999-2200-010 | 767 | 1800 | 1 | Y | 4500053417 | 50 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
35 | 145T8760-143 | On PR w/QFI????? | FILLER TAPERED | 145T8907-812 | 767 | 1800 | 8 | Y | 4500053424 | 250 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
36 | 145T8760-137 |  | FILLER TAPERED | 145T8760-803-010 | 767 | 1800 | 2 | Y | 4500053424 | 230 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
37 | 145T8760-134 |  | FILLER TAPERED | 145T8796-801-002 | 767 | 1800 | 1 | Y | 4500053424 | 210 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
38 | 145T8760-133 |  | FILLER-TAPERED | 145T8798-852 | 767 | 1800 | 12 | Y | 4500053424 | 190 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
39 | 145T8760-130 |  | FILLER-TAPERED , | 145T8760-807 | 767 | 1800 | 2 | Y | 4500053424 | 170 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
40 | 145T8721-026 |  | FILLER | 145T8721-864 | 767 | 1800 | 2 | Y | 4500053424 | 150 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
41 | 145T8721-014 |  | FILLER TAPERED | 145T8721-864 | 767 | 1800 | 4 | Y | 4500053424 | 130 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
42 | 145T2620-016 |  | FILLER | 145T2620-853-010 | 767 | 1800 | 1 | Y | 4500053424 | 110 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
43 | 145T2618-006 |  | SHIM, | 145T2620-851-003 | 767 | 1800 | 4 | Y | 4500053424 | 70 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
44 | 145T2618-002 |  | SHIM | 145T2620-853-010 | 767 | 1800 | 4 | Y | 4500053424 | 10 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
45 | 100T1481-020 |  | FILLER | 145T9999-2200-010 | 767 | 1800 | 4 | Y | 4500053417 | 30 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
46 | 100T1481-019 |  | FILLER | 145T9999-2200-010 | 767 | 1800 | 4 | Y | 4500053417 | 10 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013 | No tools
47 | 182U0008-006 |  | SHIM, TAPERED | 906C2-813KIT | 747 | 1600 | 1 | Y | 4500051961 | 60 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes | 182U0008-006 | Shipped Complete | (#3) LTA/0298/2013 | Tools at Essner
48 | 182T0100-025 |  | SHIM, (UD) | 182T3100-005-521 | 767 Common | 1600 | 22 | Y | 4500051963 | 20 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes | 182T0100-025 | Shipped Complete | (#3) LTA/0298/2013 | Tools at Essner
49 | 182T0100-024 |  | SHIM, (UD) | 182T4000-005-521 | 767 Common | 1600 | 22 | Y | 4500051963 | 10 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes | 182T0100-024 | Shipped Complete | (#3) LTA/0298/2013 | Tools at Essner
50 | 148U9123-7 |  | SHIM, | 483-3-1050 | 747 | 1600 | 5 | Y | 4500051961 | 30 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes | 148U9123-7 | Shipped Complete | (#3) LTA/0298/2013 | Tools at Essner
51 | 140U2402-133 |  | WEB | 146U5312-17-02 | 747 | 1300 | 1 | Y | 4500051430 | 130 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes | 140U2402-133 | Shipped Complete | (#3) LTA/0298/2013 | Tools at Essner
52 | 140U2402-131 |  | WEB | 146U5312-17-02 | 747 | 1300 | 1 | Y | 4500051430 | 120 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes | 140U2402-131 | Shipped Complete | (#3) LTA/0298/2013 | Tools at Essner
53 | 182U0008-004 |  | SHIM, TAPERED | 906C2-813KIT | 747 | 1600 | 1 | Y | 4500051961 | 50 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013
54 | 148U9123-47 |  | SHIM, | 483-3-2051 | 747 | 1600 | 4 | Y | 4500051961 | 20 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013
55 | 145T2618-007 |  | SHIM | 145T2620-851-003 | 767 | 1800 | 5 | Y | 4500053424 | 90 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013
56 | 145T2618-005 |  | SHIM, | 145T2620-853-010 | 767 | 1800 | 2 | Y | 4500053424 | 50 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013
57 | 145T2618-004 |  | SHIM , | 145T2620-853-010 | 767 | 1800 | 2 | Y | 4500053424 | 30 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C |  | C | C | C | Complete | Yes |  | Shipped Complete | (#3) LTA/0298/2013
58 | 65B03629-080 |  | TEE, | 906C2-832KIT | 747 | 1600 | 1 | Y | 4500051919 | 30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | On Hold | 65B03629-080 | Parts are on HOLD per Brandy G. | (#11) LTA/0304/2013 | Tools at Essner
59 | 65B03637-027-500 |  | SHEAR TIE, | 906C1-729KIT | 747 | 1600 | 1 | Y | 4500051919 | 70 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | On Hold | 65B03637-027-500 | Parts are on HOLD per Brandy G. | (#11) LTA/0304/2013 | Tools at TAVAD shipping Dock
60 | 65B03629-079 |  | TEE, | 906C1-730KIT | 747 | 1600 | 1 | Y | 4500051919 | 20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | On Hold | 65B03629-079 | Parts are on HOLD per Brandy G. | (#11) LTA/0304/2013 | Tools at TAVAD shipping Dock
61 | 65B03630-101 |  | TEE, | 906C1-730KIT | 747 | 1600 | 1 | Y | 4500051919 | 60 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | On Hold |  | Parts are on HOLD per Brandy G. | (#11) LTA/0304/2013
62 | 65B03629-084 |  | TEE, | 906C2-830KIT | 747 | 1600 | 1 | Y | 4500051919 | 50 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | On Hold |  | Parts are on HOLD per Brandy G. | (#11) LTA/0304/2013
63 | 65B03629-083 |  | TEE, | 906C1-727KIT | 747 | 1600 | 1 | Y | 4500051919 | 40 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | On Hold |  | Parts are on HOLD per Brandy G. | (#11) LTA/0304/2013
64 | 65B03628-086 |  | SHEAR TIE, | 906C2-832KIT | 747 | 1600 | 1 | Y | 4500051919 | 10 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | On Hold |  | Parts are on HOLD per Brandy G. | (#11) LTA/0304/2013
65 | 65B02968-007 |  | FAIRING,SEAL | #N/A | 747 | 1600 | X | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Romoved from SOW / At Gamma as a -7-801 | (#9) LTA/0302/2013 | N/A
66 | 65B02886-007 |  | LONGERON - AUX | #N/A | 747 | 1600 | X | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Romoved from SOW / At Gamma as a -7-801 | (#9) LTA/0302/2013 | N/A
67 | 173U3512-3-03 |  | WEB, UPPER CHORD CLOSURE | #N/A | 747 | 1600 | X | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Removed from SOW / Metal Bond Assm / T-FW Supplier | (#9) LTA/0302/2013 | N/A
68 | 173U3512-3-02 |  | WEB, UPPER CHORD CLOSURE | #N/A | 747 | 1600 | X | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Removed from SOW / Detail Part to 173U3512-3-03 (below) / T-FW Supplier | (#9) LTA/0302/2013 | N/A
69 | 173U3502-5-02 |  | WEB, | #N/A | 747 | 1600 | X | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Rolled to 173U3502-12-01 (On FAI Plan) | (#9) LTA/0302/2013 | N/A
70 | 172U3053-1-02 |  | WEB, | #N/A | 747 | 1600 | X | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Removed from SOW / PAPO to XAIC | (#9) LTA/0302/2013 | N/A
71 | 148U3528-13-01 | 148U3528-15-01 | ANGLE, | #N/A | 747 | 1600 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Rolled / Sourced to LMI | (#9) LTA/0302/2013 | N/A
72 | 145T8760-187 |  | FILLER | #N/A | 767 | 1800 | 4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Surplus Stock / No open Requirements | (#3) LTA/0298/2013 | N/A
73 | 145T8760-135 |  | FILLER TAPERED | 145T8796-801-002 | 767 | 1800 | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | Surplus Stock / No open Requirements | (#3) LTA/0298/2013 | N/A
74 | 145T8750-063 |  | SUPPORT BRACKET | #N/A | 767 | 1800 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A |  | For L/U 1068 ONLY -/ Surplus Stock / No open Requirements | (#3) LTA/0298/2013 | N/A
Note on AI21: Jace Kline: The 65B04406-608 tools: DLT 4783526-00/C00 is being looked for and the FD 4881684-00/C00 is being utilized by another part. I do believe we can get Essner both of these tools within (2) weeks.
Note on AI31: Jace Kline: 6200891-00/C00 HB 6260997-00/C01 RB 6260998-00/C00 SUT

## Transition Team Contacts
Transition Team Roles - Contacts
TGI Support Team Members | Name | Phone | E-mail | Company Name
Project Manager
Corporate Procurement
TGI Company Procurement
TGI Company Procurement
Quality
Quality
Engineering
Engineering
New Supplier Support Team Members | Name | Phone | E-mail | Company Name
Project Manager
Leadership Sponsor
Quality
Quality
Engineering
Engineering

## RAIL
RAIL
ACTION ITEM NUMBER | ASSOCIATED ACTION ITEM NUMBER | CMPT NUMBER | BUSINESS UNIT | PROGRAM | RISK REGISTER | FUNCTIONAL AREA | SUPPLIER NAME | ACTION - DESCRIPTION | COUNTERMEASURE | RAIL OWNER | ACTION OWNER | PRIORITY (Low, Medium, High) | DUE DATE | COMPLETION % | CLOSURE DATE | PROJECT STATUS Type "Complete" to highlight line | COMMENTS | PREVIOUS UPDATES | LATEST UPDATE
1 | [13 empty] | 0%
2 | [13 empty] | 0%
3 | [13 empty] | 0%
4 | [13 empty] | 0%
5 | [13 empty] | 0%
6 | [13 empty] | 0%
7 | [13 empty] | 0%
8 | [13 empty] | 0%
9 | [13 empty] | 0%
10 | [13 empty] | 0%
11 | [13 empty] | 0%
12 | [13 empty] | 0%
13 | [13 empty] | 0%
14 | [13 empty] | 0%
15 | [13 empty] | 0%
16 | [13 empty] | 0%
18 | [13 empty] | 0%
19 | [13 empty] | 0%
20 | [13 empty] | 0%
21 | [13 empty] | 0%
22 | [13 empty] | 0%
23 | [13 empty] | 0%
24 | [13 empty] | 0%
25 | [13 empty] | 0%
26 | [13 empty] | 0%
27 | [13 empty] | 0%
28 | [13 empty] | 0%
29 | [13 empty] | 0%
30 | [13 empty] | 0%
31 | [13 empty] | 0%
32 | [13 empty] | 0%
33 | [13 empty] | 0%
34 | [13 empty] | 0%
35 | [13 empty] | 0%
36 | [13 empty] | 0%
37 | [13 empty] | 0%
38 | [13 empty] | 0%
39 | [13 empty] | 0%
40 | [13 empty] | 0%
41 | [13 empty] | 0%
42 | [13 empty] | 0%
43 | [13 empty] | 0%
44 | [13 empty] | 0%
45 | [13 empty] | 0%
46 | [13 empty] | 0%
47 | [13 empty] | 0%
48 | [13 empty] | 0%
49 | [13 empty] | 0%
50 | [13 empty] | 0%
51 | [13 empty] | 0%
52 | [13 empty] | 0%
53 | [13 empty] | 0%
54 | [13 empty] | 0%
55 | [13 empty] | 0%
56 | [13 empty] | 0%
57 | [13 empty] | 0%
58 | [13 empty] | 0%
59 | [13 empty] | 0%
60 | [13 empty] | 0%
61 | [13 empty] | 0%
62 | [13 empty] | 0%
63 | [13 empty] | 0%
64 | [13 empty] | 0%
65 | [13 empty] | 0%
66 | [13 empty] | 0%
67 | [13 empty] | 0%
68 | [13 empty] | 0%
69 | [13 empty] | 0%
70 | [13 empty] | 0%
71 | [13 empty] | 0%
72 | [13 empty] | 0%
73 | [13 empty] | 0%
74 | [13 empty] | 0%
75 | [13 empty] | 0%
76 | [13 empty] | 0%
77 | [13 empty] | 0%
78 | [13 empty] | 0%
79 | [13 empty] | 0%
80 | [13 empty] | 0%
81 | [13 empty] | 0%
82 | [13 empty] | 0%
83 | [13 empty] | 0%
84 | [13 empty] | 0%
85 | [13 empty] | 0%
86 | [13 empty] | 0%
87 | [13 empty] | 0%
88 | [13 empty] | 0%
89 | [13 empty] | 0%
90 | [13 empty] | 0%
91 | [13 empty] | 0%
92 | [13 empty] | 0%
93 | [13 empty] | 0%
94 | [13 empty] | 0%
95 | [13 empty] | 0%
96 | [13 empty] | 0%
97 | [13 empty] | 0%
98 | [13 empty] | 0%
99 | [13 empty] | 0%
100 | [13 empty] | 0%
51 | [13 empty] | 100%