## SCMP 7.4 (a)
SCMP 7.4 (a) - Sourcing Project Preliminary Checklist
Considerations applicable to all Sourcing Boards- Any non-addressed item(s) must be moved to the Project RAIL SCMP 7.4 (e)
Number | Considerations | Yes/No | TGI WT Potential Actions(s) For RED Items | Base Acceptability For RED Items | Comments
1 | Will the project follow the Sourcing Board Process? | Answer | Formally request completion of a sourcing board process | Written confirmation (email acceptable) from site purchasing that SCMP 7.4 will not be followed based on execptions noted in procedure
2 | Have Programs confirmed the current forcast requirments for all parts in the proposed project | Answer | See Base Acceptability | Confirmation of forecast
3 | Has the commodity (i.e. part or equipment) and technical data been classified for export by an approved resource? | Answer | See Base Acceptability | Confirm drawings are classifed by export control
4 | If required, are the sources registered with the US State Department for the production of defense articles (US domestic) or are Manufacturing License Agreements in place that cover the transitioning parts (foreign sources)? | Answer | Confirm if any potential sources are registered with the US State Dept | Confirmation of sources registered if required
5 | Do all sources have a signed and valid NDA (Non Disclosure Agreement) with Triumph Group? | Answer | See Base Acceptability | Valid NDA in place and confirm action is closed before release of RFQ
6 | Are there any LTA clauses with the current source (Production or aftermarket) that could affect the sourcing project? (for example) (a) Exclusivity (i.e., has TGI agreed that the existing supplier will be an exclusive supplier for the part that TGI is looking to transition to a new supplier?) (b) Requirements language (i.e., is TGI required to purchase a certain percentage of its requirements from the existing supplier?) (c) Termination for Convenience – confirm such right exists for TGI and that any responsibility for loss profits is excluded. | Answer | Request data from site sourcing that there are no LTA clauses affecting the proposed parts for the sourcing Project | Review of valid LTA to confirm no commecial clauses that affect the Sourcing Project
7 | Is the Buy American Act (or any other applicable legislation - for example Berry Amendment) applicable to parts in this transition (confirm with contract specialist in answering this question - this applies to parts purchased/manufacture for a government program, even if they are dual use)? (a) If TGI certified that it will comply with the Buy American Act, is the new supplier located outside of the U.S., for Buy American considerations, and if so, do any exceptions or waivers apply (check FAR 52.225)? (b) Are there any Specialty Metal in the part to be supplied by the new supplier (check DFARs 252.225-7008 and 252.225-7009), and if so, do any exceptions apply? | Answer | Work with Contracts (Enterprise or Site) to confirm applicability of Buy American Act Did TGI certify it would comply and does the product have any speciality metals covered by DFARs? | Written confirmation (email acceptable) of any applicability
8 | Is the part Source Controlled/Customer directed/Proprietary/Sole Source part (i.e. the supplier is called out on drawing or specification)? See note | Answer | Work with Engineering and Contracts to ascertain if there are any controls that need to be followed | Confirmation that the part(s) are acceptable for the Sourcing Project
9 | Are there Intellectual Property concerns related to the manufacture of this product? (refer to hover note for explanation - detailed questions that must be considered during risk assessment, prior to any drawings/specs being sent to prospective sources) | Answer | See Base Acceptability | Joint review with Contracts and (if necessary) Engineering
10 | If funding required to execute this project For example - Tooling, NRE, Travel, ME Support etc | Answer | See Base Acceptability | Confirm with site that an NRE budget could be applied to this project
11 | Has the Supplier given an assessment of their current capacity planning tools and does it show sufficient current capacity | Answer | See Base Acceptability | Supplier to demonstrate it has a methodolgy to assess capacity planning AND demonstrates its level of open capacity
12 | Is the capability to produce the part(s) within the suppliers capabilities? | Answer | If deemed necessary by the Engineering representative of the affected site, the supplier may be assessed to demonstrate the specific capability to produce the specifc nominated parts. | Demonstrated capability based on existing supplier product portfolio or part similarity
13 | Have the preliminary personnel requirements been established for this project? | Answer | See Base Acceptability | Indentification of functional representation likely needed for project success
14 | Has project success criteria been established and agreed by stakeholders? | Answer | See Base Acceptability | Successful outcome from Stakeholder Review
15 | Could there be any financial liabilities associated with the potential transfer of work intitiated by the sourcing project? | Answer | See Base Acceptability | Work with site purchasing and contracts to identify any potential liabilities
16 | Is a "should cost" analysis be performed | Answer | See Base Acceptability | Team to determine if a baseline cost is required
Yes
No
Answer
Yes
No
N/A
Note on B12: Confirm if Special Processes or lower level components are source controlled
Note on B13: 1) Does another entity besides TGI own any IP related to the product/drawings/specs (i.e., did TGI solely design/create or was the supplier/another entity involved in the design)? 2) Did TGI use/rely on any information, not owned or created by TGI, in creating the TGI drawing/spec (e.g., did TGI use information from a supplier’s drawing, specification, data sheet, or other supplier provided document into the subject TGI drawing/spec)? 3) Were any aspects or features of the design (as illustrated in the drawing (s)) or described in the specification dictated or otherwise provided by a supplier? 4) If another entity or supplier contributed, or was involved in any way with the subject part/design/drawing/spec do we have terms in place that convey ownership in the design/drawings/specs and/or provide make and have made license rights? If the answer to any question in 1-3 is “yes” AND the answer to question 4 is “no”, then STOP. We cannot move or approve the drawings/design for quote without further IP Legal review and until all non-TGI information has been removed from all drawings/specs/etc. TGI RFQ policy must be followed.